## Gantt Chart
# | Phase | Deliverable | Owner | Start | End | Status | W1 Mar 11 | W2 Mar 18 | W3 Mar 25 | W4 Apr 01 | W5 Apr 08 | W6 Apr 15
1 | Setup | Create HF model repo | All | 2026-03-11 | 2026-03-17 | TODO
2 | Setup | Set up Colab environments | All | 2026-03-11 | 2026-03-17 | TODO
3 | Setup | Deploy aggregator Space | Lead | 2026-03-11 | 2026-03-24 | TODO
4 | Setup | Test endpoints | Lead | 2026-03-11 | 2026-03-24 | TODO
5 | Training Infra | Implement gradient hooks | All | 2026-03-18 | 2026-03-24 | TODO
6 | Training Infra | Async grad push/pull | All | 2026-03-18 | 2026-03-31 | TODO
7 | Training Infra | Round-end sync | All | 2026-03-18 | 2026-03-31 | TODO
8 | Training Infra | Test single-node loop | All | 2026-03-18 | 2026-03-31 | TODO
9 | Distributed Training | 3-node dry run | All | 2026-03-25 | 2026-03-31 | TODO
10 | Distributed Training | Verify FedAvg merge | Lead | 2026-03-25 | 2026-04-07 | TODO
11 | Distributed Training | Full training run | All | 2026-04-01 | 2026-04-07 | TODO
12 | Distributed Training | Debug staleness/spikes | All | 2026-04-01 | 2026-04-14 | TODO
13 | Distributed Training | Domain dataset integration | All | 2026-04-01 | 2026-04-14 | TODO
14 | Evaluation | Run eval prompts | All | 2026-04-08 | 2026-04-14 | TODO
15 | Evaluation | Merged vs baseline comparison | Lead | 2026-04-08 | 2026-04-14 | TODO
16 | Evaluation | Generate training plots | All | 2026-04-08 | 2026-04-14 | TODO
17 | Evaluation | Cross-domain eval | All | 2026-04-08 | 2026-04-21 | TODO
18 | Documentation | Write project report | Lead | 2026-04-08 | 2026-04-21 | TODO
19 | Documentation | Prepare demo notebook | All | 2026-04-15 | 2026-04-21 | TODO
20 | Documentation | Architecture diagram | Lead | 2026-04-15 | 2026-04-21 | TODO
21 | Buffer | Bug fixes and polish | All | 2026-04-15 | 2026-04-21 | TODO
22 | Buffer | Final submission | Lead | 2026-04-15 | 2026-04-21 | TODO